|  |  |
| --- | --- |
| Implementation Plan: xG Learn Nurse Care Coordinator/Care Coordinator Training  |  |
|  |
|  |  |  |
|  | **Major Activity** | **Result** |
|  | Pilot the selected NCM/CC RI faculty training program Action Steps 1. Develop job description and have reviewed by selection committee 1/11/17
2. Develop application process and have reviewed by selection commit 1/11/17
3. Advertise opportunity NCM meeting 1/17/17
4. Establish candidate selection committee 1/11/17
5. Interview and select candidates : 1/30-2/3/17
6. Establish and implement training schedule 2/14/17-4/30/17
 | Up to 5 Rhode Island based faculty members will complete the faculty training sessions and become certified trainers: by end of 3/31/17  |
|  |  Pilot the selected NCM/CC core curriculum 1. Establish guidelines for implementation of core curriculum for new and established NCM/CC for CTC practices and non-CTC practices by 3/15/17
2. Establish process for license authorization and practice responsibility acceptance form by 3/31/17
3. Establish Cohorts and faculty assignment by 5/15/17
 |  Up to 100 NCM will complete the standardized core NCM/CC training curriculum  |
|  |  Evaluate the results of the training programs 1. Identify potential advanced student to assist with development of evaluation plan by 2/1/17
2. Begin development of an evaluation plan : 1/24/17
3. Implement evaluation plan : 2/14/17 with end date to be determined based on evaluation plan framework
 | Evaluation survey results will be collected and analyzed including * Feedback findings from NCM/CC
* Feedback findings from faculty
* Feedback findings from practices
* Review of utilization data
* Review of module completion data
* Other?
 |
|  |  NCM/CC training will be “spread” to other primary care practice sites as part of a state-wide effort 1. Invite participation from SIM Workforce Development Committee 12/31/16
 | State-wide process will be implemented for NCM/CC training program  |