CTC-RI Contracting Committee

Agenda

|  |  |  |  |
| --- | --- | --- | --- |
| Date: Tuesday, January 10, 2017 |  | Start/End Time: 7:30am-9:00am  |  |
| **Meeting Location: Healthcentric Advisors (235 Promenade St, Suite 500. Providence)** |  | Call in number: 508-856-8222 code: 4574 (Host 8838) |  |
| MEETING INFORMATION: |  | **COMMITTEE MEMBERS/ATTENDEES: (those in attendance are identified by an \* )**  |
| Meeting Purpose/Objective: Development of the Contracts for CTC-RI |  |  |  |  |  |
|  |
|  Item # | Statement /Owner /Time | Comments | Action # |
| 1 | **M. Craig****D. Moynihan** | **Welcome and Review of Agenda** |  |
| 2 | **M. Craig****D. Hurwitz** | **Contract Updates*** Feedback on new contract template
* PCMH-Kids amendments – status of PMPM
* Adult amendments
 |  |
| 3 | **D. Hurwitz****P. Yeracaris** | **Expansion*** Small practice strategy
	+ Data driven process
	+ Target practices that did not get into CPC+
	+ RIQI – provider directory cross match to OHIC list
	+ Develop a list of questions to screen practice readiness/interest in transformation
	+ APCD – look at practice total cost of care
* Process for recruiting
 |  |
| 4 | **M. Craig****D. Moynihan** | **Next Meeting*** Next meeting to be held on Tuesday, February 14, 2017
 |  |

| ACTION ITEM LOG |
| --- |
| Date Added  | ActionNumber | Assignee | Action /Status | Due Date | Date Closed |
| 11/08/16 | 9 | Health Plans | Confirm willingness of respective organizations to post contract attachments to the website with reference in contracts | 12/13/16 |  |
| 11/08/16 | 10 | Health Plans | Confirm CPC+ participation through CTC contracts with practices | 12/13/16 |  |
| 11/08/16 | 11 | D. Moynihan | Redline list of prospective pediatric practices with any edits | 12/13/16 |  |
| 11/08/16 | 12 | Health Plans | Confirm the $3.50 PMPM for PCMH-Kids practices for expansion and current practices | 12/13/16 |  |
| 11/08/16 | 13 | M. Mobilio | Place the “calculator” for practice PMPM and costs on the CTC website  | 12/13/16 |  |
| 11/08/16 | 15 | Proj. Mgmt. | Work with OHIC to draft an audit protocol | 12/13/16 |  |
| 12/13/16 | 16 |  | Develop and send draft base contract language | 01/10/17 |  |
| 12/13/16 | 17 | Proj. Mgmt. | Set meeting with plans once final list of  | Upon release of final list |  |