PCMH-Kids Stakeholder

Minutes

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date: Thursday, Sept 1, 2016 | | |  | | Start/End Time: 7:30-8:30 am |  | |
| **Meeting Location**: 2nd floor Conf Rm, 301 Metro Center Blvd  Warwick, RI | | |  | | Call-in number: (641) 715-3580 code: 133-624 (host 2345) |  | |
| Meeting Information: | | | |  | **Co-Chairs and Speakers** | | |
| **Meeting Purpose/Objective:** Provide ongoing strategic direction of Initiative and promote the pediatric interest in committee work and overall CTC Structure  **Attachments**:   * Agenda * PCMH-Kids Lessons Learned Presentation * Directions to Metro Center | | | |  | **Patricia Flanagan, MD, FAAP, Co-Chair**  **Elizabeth Lange, MD, FAAP, Co-Chair**  **Marti Rosenberg, Project Director, SIM** | | |
|  |
|  | | | | | | | |
| Item # | Owner/Time | Comments | | | | | Action # |
| 1 | B Lange  P Flanagan  5 minutes | **Introduction** | | | | |  |
| 2 | B Lange  P Flanagan  25 minutes | **Discussion on Lessons Learned to-date in PCMH-Kids**   * Successes: improved care coordination, dedicated PCMH teams, improved work flows and processes, established documentation and reports, especially NCQA * Challenges: financial support for transformation is time-limited and infrastructure costs don’t end in Year 1, data is a huge challenge in both time and expertise, high risk lists from health plans are not specific to pediatrics, current timeline for NCQA is not realistic * Opportunities: revision of contract for new practices (increase data support, allow 21 months for NCQA submission which aligns with CTC and OHIC, allow a transition year with continued infrastructure support, flexibility in PMPM spending) and work with health plans to identify high risk patients | | | | |  |
| 3 | M Rosenberg  25 minutes | **SIM Population Health Plan**   * SIM is a $20 million grant from CMS to transform the way care is delivered and paid for * Theory of change is that by supporting providers, empowering patients, and addressing the things that influence our health (social determinants of health) we can achieve improved population health and progress towards the triple aim * SIM Integrated population health plan describes the physical and behavioral health of RI using 7 focus areas: obesity, tobacco, chronic disease, depression, children with social and emotional disturbance, serious mental illness, and opioid use disorders. We are also adding maternal and child health. * SIM will leverage its interagency structure to support collaboration across sectors—leverage resources and coordinate services to maximize the impact of existing and planned projects. * SIM questions for your consideration:   + How does SIM’s focus on Integration and Alignment as *one way* to tackle Population Health line up with your organization’s mission and work?     - Do you see opportunities to partner or collaborate?     - Who else should we talk with about SIM?     - Your questions and insights.   + What drives your programmatic decision-making in order to help children and families achieve their best health possible?   + How do you address identified barriers? Systemically? Informally? In other ways?   + Are you able to expand successful strategies and approaches?   + How is your understanding of the social determinants of heath influencing tactics, strategy and partnerships? * SIM website: <http://www.eohhs.ri.gov/Initiatives/StateInnovationModel.aspx> * SIM Steering Committee Meetings are the second Thursday of every month from 5:30-7pm at 301 Metro Center Boulevard, Warwick. Public comment is integrated throughout the meeting. | | | | |  |
| 4 | B Lange  P Flanagan  H Hakim  5 Minutes | **Other Project Management Updates**   * PCMH-Kids expansion-currently planning to delay a pediatric expansion so the state can focus on a one-time opportunity from CMS (called CPC+) which is bringing in significant dollars to practices and is a chance to bring in practices who have yet to participate in a transformation initiative to-date (CMS opportunity is limited to patients 18+). A delayed expansion also gives us time to carefully consider lessons learned and apply meaningful changes to the program that can support future pedi practices to join and succeed. Please continue to send your comments and thoughts on how we can achieve this! * Year 2 BH Learning Collaborative * PCMH-Kids Staffing-Hannah Hakim is taking a new position at EOHHS. EOHHS is providing temporary coverage to continue the important work of PCMH-Kids. Meanwhile we are securing funding for a full-time replacement to be hired by CTC. * CTC Learning Collaborative Oct 20th: <https://www.eventbrite.com/e/2016-ctc-ri-annual-learning-collaborative-advancing-primary-care-practicing-with-value-tickets-26471924238> | | | | |  |
| 5 | B Lange  P Flanagan  1 Minute | **Next Steps**   * Next Meeting Dec 1, 2016 | | | | |  |

| ACTION ITEM LOG | | | | | |
| --- | --- | --- | --- | --- | --- |
| Date Added | Action # | Assignee | Action /Status | Due  Date | Date  Closed |
|  |  |  |  |  |  |
|  |  |  |  |  |  |